## Design Risk Register
Aptoris Design Risk Register
Record significant design issues, one per row. Fill in the project details above; Status uses a dropdown. See How to Use before starting.
Project |  |  |  |  | Register revision
Design package / discipline |  |  |  |  | Review date
Register owner / coordinator
Ref | Design element / location | Foreseeable design risk / issue | Who could be affected / project stage | Design response / control | Further action required | Owner / discipline | Target date / design stage | Status | Residual information to communicate | Supporting reference
DR-001
DR-002
DR-003
DR-004
DR-005
DR-006
DR-007
DR-008
DR-009
DR-010
DR-011
DR-012
DR-013
DR-014
DR-015
DR-016
DR-017
DR-018
DR-019
DR-020
DR-021
DR-022
DR-023
DR-024
DR-025

## Worked Example
Aptoris Design Risk Register
Fictional worked examples for illustrating the register structure only.
Project |  | Example: office refurbishment and plant upgrade (fictional) |  |  | Register revision | P02
Design package / discipline |  | Architecture, structure and building services |  |  | Review date | 2026-11-12
Register owner / coordinator |  | Principal Designer (design-risk coordinator)
Ref | Design element / location | Foreseeable design risk / issue | Who could be affected / project stage | Design response / control | Further action required | Owner / discipline | Target date / design stage | Status | Residual information to communicate | Supporting reference
DR-001 | Roof: replacement air handling unit and condenser units, north-east corner | Proposed plant position puts routine filter changes and servicing within 2 m of an unprotected roof edge, so maintenance teams would repeatedly work close to an open edge. | Installers (installation); maintenance technicians (maintenance, cleaning, future replacement) | Options reviewed at the Stage 3 design-risk workshop: • relocate the units away from the edge where structure and duct routes allow • provide permanent protected access if relocation is not fully achievable • confirm maintenance clearances around service panels | • Structural engineer to confirm roof capacity at the alternative position • Architect to update the roof plan and access route • Building services designer to confirm clearances with manufacturer data | Building services designer, with architect and structural engineer | Stage 4 design review | In progress | If any maintenance zone remains near the edge, show the protected access route on the roof plan and record the access arrangements for the health and safety file. | Roof plan A-200 rev P03; plant schedule M-01; design review 04, action 14
DR-002 | Façade: east elevation cladding panels, levels 2 to 4 | Proposed panel size and weight would need a large crane close to the site boundary, lifting over the adjacent footpath, with a difficult interface at window openings. | Installers and lifting teams (installation); public on the adjacent footpath (construction); future panel replacement (maintenance, alteration) | Façade designer and architect reviewing: • reducing panel size and weight where the façade design allows • lifting provisions designed into the panels • installation sequence and window interface details | • Façade designer to issue revised panel setting-out and weights • Structural engineer to confirm fixing loads • Principal contractor input on lifting approach at the next coordination meeting | Façade designer (specialist contractor design) | Before façade package tender | Open | Panel weights, lifting provisions and intended installation sequence to be shown on the façade drawings and shared with the principal contractor; panel replacement information for the health and safety file. | Façade elevations F-310 rev P02; panel schedule F-02; coordination meeting 06, action 3
DR-003 | Substructure: new pad foundation F7, south-west plant compound | Utility survey shows an existing buried power cable crossing the proposed position of foundation F7, creating a risk of striking the cable during excavation. | Groundworkers (construction); future excavation or alteration works (alteration, demolition / removal) | Structural and building services designers coordinated using the survey information: • foundation F7 moved and redesigned to keep clear of the cable route • protection detail added where the new drainage run crosses the cable • clearance and protection agreed with the utility owner | None outstanding. Trial holes confirmed cable position and depth; utility owner confirmed clearance. | Structural engineer, with building services designer | Stage 4 foundation layout | Closed | Cable route, verified depth and protection detail shown on the foundation and drainage drawings, included in the pre-construction information for groundworks and recorded for the health and safety file. | Utility survey US-01 rev B; trial hole log TH-02; foundation layout S-110 rev P04

## How to Use
How to use the Aptoris Design Risk Register
PURPOSE
This workbook can support design-risk management and coordination. Use it to record significant design issues: what the issue is, what has been done through the design, what still needs to happen, who owns it and what residual information needs to reach others.
It is not a prescribed CDM document.
WHAT TO RECORD
Record significant design issues that:
• can be influenced through the design;
• require action;
• require coordination between designers or with contractors; or
• need relevant information communicating to others.
WHAT NOT TO RECORD
Do not turn the register into a generic hazard log. Entries such as working at height, manual handling, PPE or slips and trips should not simply be listed as generic hazards unless something particular about the design creates or materially changes the issue.
HOW TO USE THE REGISTER
1. Raise the issue early.
2. Record how the design can eliminate, reduce or control it.
3. Assign further actions clearly.
4. Review it at the appropriate design stage.
5. Communicate significant residual information through the appropriate project information.
6. Close the action when the coordinated work is complete, while retaining relevant residual information where necessary.
Closed means the action is complete. It does not mean the risk has disappeared or that a formal safety approval has been given.
PROJECT STAGE / AFFECTED PEOPLE
Use Who could be affected / project stage to note the people and stages the design issue affects, where relevant: construction, installation, commissioning, use, cleaning, maintenance, alteration and demolition or removal. One entry can name more than one stage.
USING THE SPREADSHEET
• Fill in the project details at the top of the Design Risk Register sheet.
• Status has a dropdown: Open, In progress or Closed.
• To add rows, type in the row directly below the register; the table, formatting and Status dropdown extend automatically.
• Supporting reference can record a drawing number, model reference, specification clause, design note, survey, calculation or meeting action. A hyperlink is not needed.
• The Worked Example sheet shows three fictional entries.
IMPORTANT NOTE
CDM 2015 does not prescribe a Design Risk Register or particular risk-scoring format. This workbook is a practical project tool and does not by itself demonstrate compliance with CDM 2015. Designers remain responsible for their duties under Regulation 9, and the Principal Designer has separate coordination duties under Regulation 11 where appointed.
The workbook should be adapted to the project and organisation's existing design-management arrangements.